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Sample Repair Estimate and Draw Schedule

PROPERTY:

ADDRESS:

Please complete this template in line with your project. Use this as a guide for the level of detail and scheduling in your renovation or construction project draw schedule. Following this general format and detail allows our inspection team to service your draw requests more efficiently.

Draw 1: Exterior

Detail all exterior items with cost to get property under roof

	Wrap Exterior and install new vinyl siding
	$9,000

	Install 11 new windows
	$5,000

	Re-shingle asphalt roof
	$3,000

	Total
	$17,000

	Draw 2: Rough In
	

	Detail all items needed for rough-in of mechanicals, electrical, plumbing
	

	Rough In HVAC
	$5,000

	Rough In Plumbing of new full bath upstairs and ••• bath on main level
	$10,000

	Upgrade of electrical service to house and new panel
	$3,500

	Total
	$18,500

	Draw 3: Drywall and Trim and other interior
	

	Detail all items needed for interior walls, paint, and trim
	

	Repair Drywall in living room, kitchen, and bedroom
	$2,000

	Replace Interior Doors
	$1,500

	Interior Paint
	$1,500

	Trim in living room, dining room
	$1,500

	Total
	$6,500

	Draw 4: Kitchens, Bathrooms, Flooring
	

	Detail all items needed for bathroom, kitchens, and floors
	

	Install new tile in 2 full bathrooms
	$3,000

	Install new HW Floors in living room, dining room
	$3,000

	Install new carpet in all 3 bedrooms
	$2,000

	Kitchen cabinets, countertops, and appliances installed
	$8,000

	Total
	$16,000

	Draw 5: Completion
	

	Detail all items that have been completed and needing last draw
	

	Completion HVAC
	$5,000

	Completion electrical
	$2,500

	Plumbing fixture install
	$5,000

	Total
	$12,500

	Total of Draws
	$70,500
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